DEPLOYMENT AND COMMUNICATION PLAN

RPL Upgrade, 6-Month DTS and GIS Export DTS

| Item | Task Description | Date/Time | Resources |  | Completed? |
| --- | --- | --- | --- | --- | --- |
|  |  |  | Accenture | Shelby |  |
| 1.0 | Perform pre-installation tasks and pre-UAT tasks. |  |  |  |  |
| 1.1 | Have all users exit the Reporting system. Optionally, capture any User Acceptance Testing (UAT) defined data checks and produce reports. | 06/22/07 9:00am |  | Dennis C. |  |
| 1.2 | Get permission from client to dial in. | 06/22/07 | Robert |  |  |
| 1.3 | Transfer installation files including scripts, controls and application files in preparation for installation to the Reporting Environment. | 06/22/07 | Robert |  |  |
| 2.0 | Install RPL v2.6.006. |  |  |  |  |
| 2.1 | Deploy RPL. | 06/22/07 | Robert |  |  |
| 2.2 | Perform checks to confirm installation. | 06/22/07 | Robert |  |  |
| 3.0 | Install DTS Agent Application. |  |  |  |  |
| 3.1 | Perform install of the DTS Agent Application. | 06/22/07 | Robert |  |  |
| 3.2 | Perform initial configuration. | 06/22/07 | Robert |  |  |
| 4.0 | Install 6-Month DTS. |  |  |  |  |
| 4.1 | Install 6-Month DTS in the DTS Agent Application. | 06/22/07 | Robert |  |  |
| 4.2 | Initialize parameters. | 06/22/07 | Robert |  |  |
| 4.3 | Perform a test run to verify installation. | 06/22/07 | Robert |  |  |
| 5.0 | Install GIS Export DTS. |  |  |  |  |
| 5.1 | Install GIS Export DTS in the DTS Agent Application. | 06/22/07 | Robert |  |  |
| 5.2 | Initialize parameters. | 06/22/07 | Robert |  |  |
| 5.3 | Perform a test run to verify installation. | 06/22/07 | Robert |  |  |
| 5.4 | Notify client of readiness to test. | 06/22/07 | Robert |  |  |
| 6.0 | Conduct User Acceptance Testing (up to 3 days). |  |  |  |  |
| 3.1 | Conduct UAT against each of the new deliverables. | 06/22/07 – 06/26/07 |  | Shelby (multiple users) |  |
| 3.2 | If issues are found, complete the SIR Log and provide to Accenture. | 06/22/07 – 06/26/07 | Christy | Dennis Boyce |  |
| 3.3 | Confirm acceptance of deliverables to Accenture. | 06/26/07 |  | Dennis Boyce |  |
| 3.4 | Copy RPL.MDE into Voter Folder on Production. | 06/27/07 | Robert |  |  |
| 3.5 | Run the Voter Update on each workstation. | 06/27/07 |  | Dennis Boyce |  |